## Task Update Sheet
Task | Project Lead | Start Date | End Date | Progress | Status
Planning Stage |  |  |  |  | Part 1 | Part 2 | Part 3 | Part 4 | Part 5 | Part 6
Task 1 (P) | Deepa | 2024-08-01 | 2024-11-30 | 66.67% | Done | Done | Pending | Done | Pending | Done
Task 2 (P) | Deldan | 2024-08-02 | 2024-12-01 | 100% | Done | Done | Done | Done | Done | Done
Task 3 (P) | Diksha | 2024-08-03 | 2024-12-02 | 100% | Done | Done | Done | Done | Done | Done
Task 4 (P) | Rohit Sir | 2024-08-04 | 2024-12-03 | 50% | Done | Done | Pending | Pending | Pending | Done
Task 5 (P) | Deepika Mam | 2024-08-05 | 2024-12-04 | 83.33% | Done | Done | Done | Done | Done | Pending
Execution Stage |  |  |  |  | Done | Done | Done | Done | Done | Done
Task 1 (E) | Deepa | 2024-12-05 | 2025-03-19 | 16.67% | Done | Pending | Pending | Pending | Pending | Pending
Task 2 (E) | Deldan | 2024-12-06 | 2025-03-20 | 100% | Done | Done | Done | Done | Done | Done
Task 3 (E) | Diksha | 2024-12-07 | 2025-03-21 | 100% | Done | Done | Done | Done | Done | Done
Task 4 (E) | Rohit Sir | 2024-12-08 | 2025-03-22 | 100% | Done | Done | Done | Done | Done | Done
Task 5 (E) | Deepika Mam | 2024-12-09 | 2025-03-23 | 100% | Done | Done | Done | Done | Done | Done
Review Stage |  |  |  |  | Done | Done | Done | Pending | Done | Done
Task 1 (R) | Deepa | 2025-03-24 | 2025-04-30 | 100% | Done | Done | Done | Done | Done | Done
Task 2 (R) | Deldan | 2025-03-25 | 2025-05-01 | 100% | Done | Done | Done | Done | Done | Done
Task 3 (R) | Diksha | 2025-03-26 | 2025-05-02 | 83.33% | Done | Done | Pending | Done | Done | Done
Task 4 (R) | Rohit Sir | 2025-03-27 | 2025-05-03 | 33.33% | Pending | Done | Pending | Done | Pending | Pending
Task 5 (R) | Deepika Mam | 2025-03-28 | 2025-05-04 | 100% | Done | Done | Done | Done | Done | Done
Final Stage |  |  |  |  | Done | Done | Done | Done | Done | Done
Task 1 (F) | Deepa | 2025-05-05 | 2025-05-26 | 83.33% | Done | Done | Done | Done | Done | Pending
Task 2 (F) | Deldan | 2025-05-06 | 2025-05-27 | 16.67% | Done | Pending | Pending | Pending | Pending | Pending
Task 3 (F) | Diksha | 2025-05-07 | 2025-05-28 | 100% | Done | Done | Done | Done | Done | Done
Task 4 (F) | Rohit Sir | 2025-05-08 | 2025-05-29 | 100% | Done | Done | Done | Done | Done | Done
Task 5 (F) | Deepika Mam | 2025-05-09 | 2025-05-30 | 66.67% | Done | Done | Done | Pending | Pending | Done

## Gantt Chart
Project Name | Vivaldi Antenna
Project Start Date | 2024-08-01
Current Date | 2025-05-23
Weeks in Progress | 43
Days in Progress | 295
Task | Project Lead | Start Date | End Date | Days | Progress | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-12 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Planning Stage
Task 1 (P) | Deepa | 2024-08-01 | 2024-11-30 | 122 | 66.67%
Task 2 (P) | Deldan | 2024-08-02 | 2024-12-01 | 122 | 100%
Task 3 (P) | Diksha | 2024-08-03 | 2024-12-02 | 122 | 100%
Task 4 (P) | Rohit Sir | 2024-08-04 | 2024-12-03 | 122 | 50%
Task 5 (P) | Deepika Mam | 2024-08-05 | 2024-12-04 | 122 | 83.33%
Execution Stage
Task 1 (E) | Deepa | 2024-12-05 | 2025-03-19 | 105 | 16.67%
Task 2 (E) | Deldan | 2024-12-06 | 2025-03-20 | 105 | 100%
Task 3 (E) | Diksha | 2024-12-07 | 2025-03-21 | 105 | 100%
Task 4 (E) | Rohit Sir | 2024-12-08 | 2025-03-22 | 105 | 100%
Task 5 (E) | Deepika Mam | 2024-12-09 | 2025-03-23 | 105 | 100%
Review Stage
Task 1 (R) | Deepa | 2025-03-24 | 2025-04-30 | 38 | 100%
Task 2 (R) | Deldan | 2025-03-25 | 2025-05-01 | 38 | 100%
Task 3 (R) | Diksha | 2025-03-26 | 2025-05-02 | 38 | 83.33%
Task 4 (R) | Rohit Sir | 2025-03-27 | 2025-05-03 | 38 | 33.33%
Task 5 (R) | Deepika Mam | 2025-03-28 | 2025-05-04 | 38 | 100%
Final Stage
Task 1 (F) | Deepa | 2025-05-05 | 2025-05-26 | 22 | 83.33%
Task 2 (F) | Deldan | 2025-05-06 | 2025-05-27 | 22 | 16.67%
Task 3 (F) | Diksha | 2025-05-07 | 2025-05-28 | 22 | 100%
Task 4 (F) | Rohit Sir | 2025-05-08 | 2025-05-29 | 22 | 100%
Task 5 (F) | Deepika Mam | 2025-05-09 | 2025-05-30 | 22 | 66.67%
Note on C3: Diksha: Put start date here